## Sheet1
Committed Backlog Items | Not Started | Commited |  | Done | Date | 2020-04-16
Voting Functions Algorithms | Test Plurality | Test STV system | Chris
As Customer, |  | Develop Plurality | Gab
I want a fully functional election system, |  | Test Ballot Box | Chris
fixed from project 1.
System Testing
Acceptance and Done Criteria
Droop and Plurality quota work as specified;
Effort Medium
Shuffle Functionality | Not Started | Commited |  | Done
As Customer, |  | Reaserch Rand() | Adam
I want the shuffle function to properly shuffle |  | Develop Shuffle | Adam
votes when engaged | Test Shuffle
Acceptance and Done Criteria
shuffle shuffles votes when engaged.
Effort Low
GUI user processes | Not Started | Commited |  | Done
As Customer, I want a GUI for all user processes of the software |  | Learn GUI Framework | Patrick
|  | Add user Input | Patrick
Acceptance and Done Criteria | ELection Results
GUI developed for the main menu, help screen | Help Screen
inputs from the user, and result of an election. | Implement GUI with algorthim
Effort Large
Ballot Validity Check | Not Started | Commited |  | Done
How System will Work
As Customer, I want the system to check all ballots for validity and not include ballots in the election that are considered invalid (ie have ranked fewer than half of all candidates) | Code
Testing
Acceptance and Done Criteria | Implmentation
The system can check differentiate between
valid and invalid ballots
Effort Small
Ballot Validity Election Check | Not Started | Commited |  | Done
How System will Work
As Customer, | Code
I want the system to be able to not | Testing
run an election if over half the ballots are invalid. | Implmentation
Acceptance and Done Criteria
The system can check the validity of all ballots
Effort Small