## Sheet1
Committed Backlog Items | Not Started | Commited |  | Done |  | Date | 2020-04-27
Voting Functions Algorithms |  |  |  | Develop Plurality | Gab
As Customer, |  |  |  | Test Ballot Box | Chris
I want a fully functional election system, |  |  |  | Test STV system | Adam
fixed from project 1. |  |  |  | Test Plurality | Adam
|  |  |  | System Testing | Adam
Acceptance and Done Criteria
Droop and Plurality quota work as specified;
Effort Medium
Shuffle Functionality | Not Started | Commited |  | Done
As Customer, |  | Documentation | Although testing has been done - better documentation needed for next week | Reaserch Rand() | Adam
I want the shuffle function to properly shuffle |  |  |  | Develop Shuffle | Adam
votes when engaged |  |  |  | Test Shuffle | Adam
Acceptance and Done Criteria
shuffle shuffles votes when engaged.
Effort Low
GUI user processes | Not Started | Commited |  | Done
As Customer, I want a GUI for all user processes of the software |  |  |  | Learn GUI Framework | Patrick
|  |  |  | Add user Input | Patrick
Acceptance and Done Criteria |  |  |  | Election Results | Patrick
GUI developed for the main menu, help screen |  |  |  | Help Screen | Patrick
inputs from the user, and result of an election. |  |  |  | Implement GUI with algorthim | Patrick
Effort Large
Ballot Validity Check | Not Started | Commited |  | Done
|  | Documentation | Although testing has been done - better documentation needed for next week | How System will Work | Adam
As Customer, I want the system to check all ballots for validity and not include ballots in the election that are considered invalid (ie have ranked fewer than half of all candidates) |  |  |  | Code | Adam
|  |  |  | Testing | Adam
Acceptance and Done Criteria |  |  |  | Implmentation | Adam
The system can check differentiate between
valid and invalid ballots
Effort Small
Ballot Validity Election Check | Not Started | Commited |  | Done
|  | Documentation | Although testing has been done - better documentation needed for next week | How System will Work | Adam
As Customer, |  |  |  | Code | Adam
I want the system to be able to not |  |  |  | Testing | Adam
run an election if over half the ballots are invalid. |  |  |  | Implmentation | Adam
Acceptance and Done Criteria
The system can check the validity of all ballots
Effort Small